INTELLI PLATFORM

MVP Plan of Action

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Fidelis Digital  •  2-Week Sprint  •  4 Developers
64 Features  •  3 Products

March 2026

# 1. Project Overview

Intelli Platform is Fidelis Digital's suite of AI-native enterprise products. The MVP sprint delivers the shared platform core along with two product verticals — Intelli Depot (warehouse & logistics) and a focused slice of Intelli Stream (financial intelligence).

## MVP Products

| Product | Description | Target Users |
| --- | --- | --- |
| Intelli Platform (Core) | Shared services — Auth, AI, Data, Notifications, Observability | All products |
| Intelli Depot™ | AI-powered warehouse & logistics management with computer vision | Warehouse Operations |
| Intelli Stream™ | CFO intelligence — Credit Rating + Distress Probability only | Finance & Treasury |

Not in MVP: Intelli Cafe, Intelli Recruit — deferred to post-MVP.

# 2. Architecture — 7-Layer Model

The platform follows a layered architecture built top-down. Higher layers (AI, Platform Services) are built first so product-specific features can leverage them.

| Layer | Name | What It Contains |
| --- | --- | --- |
| 7 | AI Orchestration Brain | LLM routing, multi-agent framework, RAG, prompt management, explainability |
| 6 | Common Platform Services | Auth/RBAC, API Gateway, Notifications, Analytics, Observability, Real-Time |
| 5 | Data Infrastructure | Database, Vector DB, File Storage, Data Warehouse connectors |
| 4 | Integration Layer | Enterprise connectors (REST APIs, webhooks, circuit breakers) |
| 3 | Command / Operations | Product-specific business logic (Depot Command, Stream RiskRadar) |
| 2 | Module-Specific Features | Vision, Inventory, Operations, Orchestrator |
| 1 | User Experience | Dashboards, UI components, mobile-responsive design |

Build order: Layers 7 → 6 → 5 → 4 (foundation first), then product features (Layers 3–1) in parallel.

# 3. Team & Responsibilities

| Developer | Focus Area | Key Deliverables |
| --- | --- | --- |
| @Suraj | AI / Backend Core | AI Orchestration, RBAC, Notifications, Stream, Depot Vision |
| @Chetan | Data & Analytics | Data infrastructure, Analytics engines, Gateway, Depot Command |
| @Keerthi | Frontend & UX | UI shell, Dashboards, Real-Time Engine, Security |
| @Pranishree | Ops & Quality | Observability, Shared utilities, Depot Operations, Testing |

# 4. Feature Breakdown by Category

The MVP consists of 64 features (6 already built, 58 to build) organized across 9 categories.

| Category | Built | To Build | Total |
| --- | --- | --- | --- |
| DevOps & Foundation | 1 | 1 | 2 |
| AI Orchestration (Layer 7) | 3 | 2 | 5 |
| Platform Services (Layer 6) | 1 | 20 | 21 |
| Data Infrastructure (Layer 5) | 1 | 3 | 4 |
| Integration (Layer 4) | — | 1 | 1 |
| Shared Utilities | — | 3 | 3 |
| Frontend UI | — | 4 | 4 |
| Intelli Depot | — | 21 | 21 |
| Intelli Stream | — | 3 | 3 |
| TOTAL | 6 | 58 | 64 |

### AI Orchestration (Layer 7)

AI-7.1: LLM Orchestration Engine — multi-model routing, fallback, cost tracking

AI-7.2: Multi-Agent Framework — agent lifecycle, task delegation, pipelines

AI-7.3: RAG Framework — vector DB integration, chunking, embedding pipeline

AI-7.4: Prompt Management — templates, versioning, A/B testing

AI-7.5: Explainability Engine — decision audit trails, confidence scoring

### Platform Services (Layer 6)

### Auth & Security

AUTH-6.1: Authentication System — JWT, login/logout, sessions

AUTH-6.2: RBAC — Roles, permissions, policy engine, multi-tenant

SEC-6.22: Security & Encryption — AES-256 at rest, TLS 1.3, key rotation

### API & Platform Infrastructure

GW-6.5: Unified API Gateway — rate limiting, routing, versioning, logging

PLAT-6.25: Modular Architecture — module registry, feature toggles, dependency mapping

PLAT-6.26: Real-Time Engine — WebSocket, SSE, pub/sub, auto-reconnect

PLAT-6.23: No-Code Configuration Engine — rules engine, configurable thresholds

### Notifications

NOTIF-6.7: Notification Engine Core — templates, delivery queue, retry, tracking

NOTIF-6.12: In-App Notifications — WebSocket real-time, notification center

### Analytics & Intelligence

ANLY-6.15: Predictive Analytics Engine — forecasting, trend & anomaly detection

ANLY-6.16: Simulation Engine — what-if scenarios, Monte Carlo, sensitivity analysis

ANLY-6.17: Executive Dashboards — configurable widgets, real-time data, export

ANLY-6.22: Sentiment Analysis — basic positive/negative/neutral (MVP scope)

ANLY-6.23: ROI & Performance Tracking — basic KPI cards (MVP scope)

ANLY-6.24: Report Generation — PDF export, 1 template (MVP scope)

ANLY-6.25: Orchestrator Agent — cross-domain insights, priority arbitration

AI-MODEL: AI Model Management — model registry listing (MVP scope)

### Observability

OBS-6.18: Audit Logging — immutable audit trail, compliance reporting

OBS-6.19: Application Monitoring — health checks, metrics, alerting, tracing

OBS-6.20: SLA Monitoring — performance tracking, breach prediction

### Data Infrastructure (Layer 5)

DATA-5.1: Database Setup — PostgreSQL, SQLAlchemy, Alembic, connection pooling

DATA-5.2: Vector Database Layer — Pinecone/Weaviate, semantic search API

DATA-5.4: Data Warehouse Connector — Snowflake/BigQuery, data sync

DATA-5.6: File Storage Service — S3/MinIO abstraction, presigned URLs

### Integration (Layer 4)

INT-4.1: Enterprise Data Connectors — REST API framework, webhooks, circuit breaker

### Shared Utilities & Frontend

SHARED-1: Base Models & Schemas — Pydantic schemas, SQLAlchemy mixins, pagination

SHARED-2: Common Middleware — CORS, request ID, rate limiting, error handling

SHARED-3: Multi-Language Support — English + Arabic UI labels (MVP scope)

UI-1: App Shell & Navigation — layout, sidebar, header, product switcher

UI-2: Design System — Tailwind + shadcn/ui, theme, common components

UI-3: Login & Auth Pages — login, register, forgot password, MFA

UI-4: User Profile & Settings — profile page, preferences, notifications

### Intelli Depot — 21 Features

IntelliVision (Computer Vision):

DEPOT-V1: Camera Feed Integration — RTSP/IP streams, frame extraction

DEPOT-V2: Bag/Box Detection — YOLO v8 detection, counting, size estimation

DEPOT-V3: Automated Counting — real-time tally, discrepancy alerts

DEPOT-V4: Cluster Mapping — space heatmap, occupancy, zone management

DEPOT-V5: FIFO/FILO/LIFO Logic — stack ordering, age-based prioritization

DEPOT-V7: Perimeter Monitoring — breach detection, unauthorized access alerts

Inventory & Operations:

DEPOT-INV1: Inventory Management Core — SKU, stock levels, barcode/QR

DEPOT-OPS1: Task Assignment — manual assignment with priority queue (MVP)

DEPOT-OPS2: Guided Checklists — static templates, completion tracking (MVP)

Command Layer:

DEPOT-CMD1: Live Monitoring — multi-feed dashboard, threshold alerts

DEPOT-CMD2: Fleet & Yard View — fleet tracking, yard slots, dwell time

DEPOT-CMD3: Incident Escalation — auto-escalation, severity, multi-channel alerts

DEPOT-CMD4: SLA Tracking — breach prediction, performance scoring

Analytics & Orchestrator:

DEPOT-ANLY1: Operational KPIs — throughput, utilization, cost-per-unit

DEPOT-ANLY3: RBAC & Audit Logs — depot-specific access, tamper-proof trails

DEPOT-ANLY-AD: Anomaly Detection — operations anomalies, fraud detection

DEPOT-INT3: API Health Monitoring — health checks, latency, error rate

DEPOT-ORCH1: Cross-Module Optimization — multi-objective, recommendations

DEPOT-ORCH2: Scenario Simulation — variable adjustment, impact visualization

DEPOT-ORCH-RL: Revenue Leakage Detection — root cause, recovery recommendations

Dashboard:

DEPOT-DASH1: Warehouse Dashboard — real-time overview, KPIs, alerts

### Intelli Stream — 3 Features (MVP Slice)

STR-RR1: Credit Rating Monitoring — tracking, alerts, counterparty exposure

STR-RR2: Distress Probability — Z-score, cash flow stress testing, default probability

STR-DASH: Stream Dashboard — credit rating + distress probability view

# 5. Day-by-Day Sprint Plan

The 2-week sprint (10 working days) is structured so that foundation layers are built first, unlocking product-specific features in parallel during the second half.

## WEEK 1 — Foundation & Core Services

### Day 1 (Monday) — Foundation Sprint

| Developer | Feature(s) | Details |
| --- | --- | --- |
| @Suraj | AUTH-6.2: RBAC | Roles, permissions, policy engine — many features depend on this |
| @Chetan | DATA-5.2: Vector DB DATA-5.6: File Storage | Both have no dependencies, start immediately |
| @Keerthi | UI-1: App Shell UI-2: Design System | Frontend foundation — layout, sidebar, components |
| @Pranishree | SHARED-1: Base Models SHARED-2: Middleware DEVOPS-3: Docker | Shared utilities + Docker local dev setup |

### Day 2 (Tuesday) — Core Services

| Developer | Feature(s) | Details |
| --- | --- | --- |
| @Suraj | AI-7.5: Explainability AI-7.3: RAG (start) | XAI engine + begin RAG framework |
| @Chetan | GW-6.5: API Gateway PLAT-6.25: Modular Architecture | Gateway routing + module registry |
| @Keerthi | PLAT-6.26: Real-Time Engine SEC-6.22: Security | WebSocket/SSE + encryption layer |
| @Pranishree | OBS-6.18: Audit Logging OBS-6.19: App Monitoring | Full observability stack |

### Day 3 (Wednesday) — Analytics Foundation + Depot Start

| Developer | Feature(s) | Details |
| --- | --- | --- |
| @Suraj | AI-7.3: RAG (finish) NOTIF-6.7: Notifications | Complete RAG + notification engine |
| @Chetan | ANLY-6.15: Predictive Analytics DATA-5.4: DW Connector | Analytics engine foundation |
| @Keerthi | UI-3: Login Pages ANLY-6.17: Dashboards (start) | Auth UI + dashboard framework |
| @Pranishree | DEPOT-V1: Camera Feed DEPOT-INV1: Inventory Core | Depot product begins! |

### Day 4 (Thursday) — Analytics + Depot Vision

| Developer | Feature(s) | Details |
| --- | --- | --- |
| @Suraj | NOTIF-6.12: In-App Notifications ANLY-6.22: Sentiment | Real-time notifications + basic sentiment |
| @Chetan | ANLY-6.16: Simulation Engine INT-4.1: Enterprise Connectors | What-if scenarios + API connector framework |
| @Keerthi | ANLY-6.17: Dashboards (finish) UI-4: User Profile | Complete dashboards + profile pages |
| @Pranishree | DEPOT-V2: Bag/Box Detection DEPOT-V7: Perimeter | YOLO model setup — full day focus |

### Day 5 (Friday) — Depot Operations + Platform

| Developer | Feature(s) | Details |
| --- | --- | --- |
| @Suraj | ANLY-6.25: Orchestrator Agent AI-MODEL: Model Mgmt | Central coordination + model registry |
| @Chetan | ANLY-6.23: ROI Tracking ANLY-6.24: Reports | KPI cards + PDF report export |
| @Keerthi | PLAT-6.23: No-Code Engine DEPOT-INT3: API Health | Configuration engine + API monitoring |
| @Pranishree | DEPOT-OPS1: Task Assignment DEPOT-OPS2: Checklists OBS-6.20: SLA Monitoring | Depot operations + SLA monitoring |

## WEEK 2 — Product Features, Integration & Polish

### Day 6 (Monday) — Depot Command Layer

| Developer | Feature(s) | Details |
| --- | --- | --- |
| @Suraj | DEPOT-V4: Cluster Mapping DEPOT-V5: FIFO/LIFO (start) | Space heatmap + stack ordering rules |
| @Chetan | DEPOT-CMD1: Live Monitoring DEPOT-CMD3: Escalation DEPOT-CMD4: SLA Tracking | Full command layer |
| @Keerthi | DEPOT-DASH1: Warehouse Dashboard DEPOT-CMD2: Fleet & Yard | Depot UI + fleet management |
| @Pranishree | DEPOT-V3: Counting DEPOT-ANLY3: Audit SHARED-3: i18n | Counting + audit trails + EN/AR support |

### Day 7 (Tuesday) — Depot Analytics + Stream Start

| Developer | Feature(s) | Details |
| --- | --- | --- |
| @Suraj | DEPOT-V5: FIFO/LIFO (finish) STR-RR1: Credit Rating | Complete vision + Stream begins! |
| @Chetan | DEPOT-ANLY1: Operational KPIs DEPOT-ANLY-AD: Anomaly Detection | KPI metrics + anomaly detection |
| @Keerthi | Dashboard polish + frontend integration testing | Connect all Depot components to dashboard |
| @Pranishree | Test Depot vision + operations pipeline | E2E: camera → detection → counting |

### Day 8 (Wednesday) — Stream + Depot Orchestrator

| Developer | Feature(s) | Details |
| --- | --- | --- |
| @Suraj | STR-RR2: Distress Probability | Financial distress scoring, Z-score modeling |
| @Chetan | DEPOT-ORCH1: Cross-Module Optimization | Multi-objective optimization + recommendations |
| @Keerthi | STR-DASH: Stream Dashboard | Credit rating + distress probability UI |
| @Pranishree | Integration testing — Depot operations flow | Task → checklist → monitoring → escalation |

### Day 9 (Thursday) — Orchestrator + Stretch

| Developer | Feature(s) | Details |
| --- | --- | --- |
| @Suraj | DEPOT-ORCH2: Scenario Simulation DEPOT-ORCH-RL: Revenue Leakage | Simulation + leakage detection |
| @Chetan | WF-6.13: Workflow Automation [STRETCH] | Build only if on track |
| @Keerthi | Polish all dashboards + responsive testing | Executive, Depot, Stream dashboards |
| @Pranishree | End-to-end testing all Depot features | Full workflow testing with mock data |

### Day 10 (Friday) — Integration, Testing & Polish

| Developer | Feature(s) | Details |
| --- | --- | --- |
| @Suraj | Cross-product integration testing | Test AI orchestration across all products |
| @Chetan | Analytics pipeline testing | Predictive → simulation → reports flow |
| @Keerthi | UI polish, error states, loading states | Final frontend pass |
| @Pranishree | Full regression testing + documentation | End-to-end everything |

# 6. Technology Stack

| Layer | Technology | Purpose |
| --- | --- | --- |
| Backend | Python 3.11+, FastAPI | API framework |
| Backend | SQLAlchemy 2.0 + Alembic | ORM & migrations |
| Backend | Celery + Redis | Task queue & caching |
| Frontend | React 18+ with TypeScript | UI framework |
| Frontend | Zustand | State management |
| Frontend | Tailwind CSS + shadcn/ui | Styling & components |
| Frontend | Axios + React Query | API client |
| AI / ML | Custom LLM Engine | Multi-model orchestration |
| AI / ML | Pinecone / Weaviate | Vector database |
| AI / ML | YOLO v8 + OpenCV | Computer vision (Depot) |
| AI / ML | spaCy, HuggingFace | NLP processing |
| Infra | PostgreSQL 15+ | Primary database |
| Infra | Elasticsearch | Search |
| Infra | S3 / MinIO | File storage |
| Infra | Docker + Docker Compose | Containerization |
| Testing | pytest, Vitest, Playwright | Backend, frontend, E2E |

# 7. Sprint Timeline Summary

| Phase | Days | Focus | Outcome |
| --- | --- | --- | --- |
| Foundation | Day 1 | Auth, Data, UI Shell, Shared Utils | All teams can build independently |
| Core Services | Day 2 | AI, Gateway, Real-Time, Observability | Platform services available |
| Analytics + Depot Start | Day 3–4 | Analytics engines, Vision, Inventory | Depot product underway |
| Operations + Platform | Day 5 | Depot Ops, Reports, Configuration | Week 1 wrap-up |
| Depot Command | Day 6 | Live monitoring, Fleet, Escalation | Command layer complete |
| Analytics + Stream | Day 7 | KPIs, Anomaly, Credit Rating | Stream begins |
| Stream + Orchestrator | Day 8 | Distress, Cross-module optimization | All features coded |
| Stretch + Polish | Day 9 | Orchestrator completion, Stretch goals | Feature freeze |
| Testing & Integration | Day 10 | E2E testing, bug fixes, polish | MVP ready |

# 8. Key Principles

One Feature = One Branch = One Person — no overlap, no conflicts.

Build Top-Down — Layers 7→6→5→4 first, then product features in parallel.

Dependencies Are Strict — never start a feature until all its dependencies are complete.

Orange = Reduced Scope — 7 features have simplified MVP scope to keep the sprint on track.

Test As You Go — unit tests with every feature; integration testing in Week 2.

Push Early, Push Often — claim features immediately, update status after completion.

— End of MVP Plan of Action —